## 1Semester
1st Semester
[6 empty] | Period Highlight: |  |  |  |  | 55 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT | PERIODS
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | February | [9 empty] | March | [9 empty] | April | [9 empty] | May | [9 empty] | June | [9 empty] | July
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
State of the art | 1 | 10 | 1 | 10 | 100%
Operators more representative - Analyse | 5 | 5 | 5 | 5 | 100%
Parser tools - Analyse | 7 | 10 | 7 | 10 | 100%
Test SAFE tool | 9 | 5 | 9 | 5 | 100%
Study Eclipse CDT Flow | 12 | 10 | 12 | 10 | 100%
Implement operators in Eclipse CDT | 16 | 15 | 16 | 15 | 100%
Study other operators | 19 | 5 | 19 | 5 | 100%
Modify recursive to visitor pattern | 31 | 10 | 31 | 10 | 100%
Write intermediate report | 41 | 10 | 41 | 10 | 100%
Describe future work | 48 | 3 | 48 | 3 | 100%
Prepare presentation | 49 | 7 | 49 | 7 | 100%

## 2Semester
2nd Semester
[6 empty] | Period Highlight: |  |  |  |  | 0 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT | PERIODS
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | September | [9 empty] | October | [9 empty] | November | [9 empty] | December | [9 empty] | January | [9 empty] | February
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Operators and contraints - Implementation | 1 | 20
Evaluate methods - Implementation | 1 | 20
Second stage of implementation | 21 | 20
Experiments | 25 | 20
Final report | 41 | 10