## gantt 1semestre
1º Semestre
[8 empty] | Destaque de Período: | [6 empty] | 1 |  |  |  | Plano |  |  |  | Real |  |  | % Concluída |  |  |  |  | Real (para além do plano) | [8 empty] | % Concluída (para além do plano)
| PLANO | PLANO | REAL | REAL | PERCENTAGEM | PERÍODOS
ATIVIDADE | INÍCIO | DURAÇÃO | INÍCIO | DURAÇÃO | CONCLUÍDA | Mês 1 | [9 empty] | Mês 2 | [9 empty] | Mês 3 | [9 empty] | Mês 4 | [9 empty] | Mês 5 | [9 empty] | Mês 6
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Estado da arte | 1 | 10 | 1 |  | 10%
Levantamento de requisitos | 1 | 10 | 1 | 0 | 0%
Contacto com tecnologias de Virtualização
Aplicações para a Cloud
Desafios de Segurança e Confiabilidade
Formulação clara e concisa dos objetivos a alcançar
Construção do ambiente Cloud | 11 | 30 |  |  | 0%
Seleção da plataforma de virtualização
Instalação da plataforma de virtualização
Integração de ferramentas de avaliação | 11 | 30 |  |  | 0%
Introdução de falhas muito simples
Experiências com as ferramentas e resultados
Relatório intermédio | 41 | 10 |  |  | 0%
Preparar apresentação pública para discussão
Descrever trabalho a realizar no semestre seguinte

## gantt 2semestre
2º Semestre
[8 empty] | Destaque de Período: | [6 empty] | -1 |  |  |  | Plano |  |  |  | Real |  |  | % Concluída |  |  |  |  | Real (para além do plano) | [8 empty] | % Concluída (para além do plano)
| PLANO | PLANO | REAL | REAL | PERCENTAGEM | PERÍODOS
ATIVIDADE | INÍCIO | DURAÇÃO | INÍCIO | DURAÇÃO | CONCLUÍDA | Mês 1 | [9 empty] | Mês 2 | [9 empty] | Mês 3 | [9 empty] | Mês 4 | [9 empty] | Mês 5 | [9 empty] | Mês 6
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Desenho de meios de avaliação | 1 | 20 |  |  | 0%
Implementação de meios de avaliação | 1 | 20 |  |  | 0%
Segunda fase de integração das ferramentas | 21 | 20 |  |  | 0%
Relatório final | 41 | 10 |  |  | 0%

## riscos
Risc Area | Preventative Measures | Recovery Measures
Equipment Failure | Ensure regular maintenance is undertaken | Use alternative sources/type of equipment as appropriate
Allow for sufficient funding for repairs
Indentify alternative sources/type of equipment
Data lost | Back-up data regularly
Publication of similar research | Regularly search electronic publications databases | Modify project
Continue literature review throughout candidature
Ensure timely submission
Personal issues interfere with progress | Take leave of absence (unless for sickness or bereavement) | Re-apply for admission when able to commit
Take annual leave
Take sick leave
Communicate with supervisor
Student loses interest | Select motivating topic at the start
Enrolling area ensures a dynamic research culture
Improve communication between student and supervisor
Look for warning signs
Register for support programs/seminars
Talk to fellow students in research area
Dispute between student and supervisor | Understand each other's roles and expectations
Agree on dispute resolution process when initiating relationship
Supervisor takes excessive time to check final drafts | Supervisor to plan out workload
Student plan ahead to ensure supervisor will be available
Student/Supervisor to review chapters/sections at regular intervals
Student wants to submit thesis without supervisor approval | Student to be counselled regarding implications - a recomendation of fail or major revision from examiners likely if thesis below standard | Review of thesis by alternative person within University recommended
Student leaves for employment / fails to complete on time fails to complete on time | Apply for completion scholarship/other scholarship extensions | Re-apply for admission when able to commit time to thesis
Convert to part-time/reschedule timeline
Take leave of absence when progress too slow
Submit extension of time to submit thesis form
Eliminate time consuming/low priority tasks if possible
Withdraw from the course