## gantt 1semestre
1º Semestre
[8 empty] | Destaque de Período: | [6 empty] | 1 |  |  |  | Plano |  |  |  | Real |  |  | % Concluída |  |  |  |  | Real (para além do plano) | [8 empty] | % Concluída (para além do plano)
| PLANO | PLANO | REAL | REAL | PERCENTAGEM | PERÍODOS
ATIVIDADE | INÍCIO | DURAÇÃO | INÍCIO | DURAÇÃO | CONCLUÍDA | Mês 1 | [9 empty] | Mês 2 | [9 empty] | Mês 3 | [9 empty] | Mês 4 | [9 empty] | Mês 5 | [9 empty] | Mês 6
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Estado da arte | 1 | 10 | 1 |  | 10%
Levantamento de requisitos | 1 | 10 | 1 |  | 0%
Contacto com tecnologias de Virtualização
Aplicações para a Cloud
Desafios de Segurança e Confiabilidade
Formulação clara e concisa dos objetivos a alcançar
Construção do ambiente Cloud | 11 | 30 |  |  | 0%
Seleção da plataforma de virtualização
Instalação da plataforma de virtualização
Integração de ferramentas de avaliação | 11 | 30 |  |  | 0%
Introdução de falhas muito simples
Experiências com as ferramentas e resultados
Relatório intermédio | 41 | 10 |  |  | 0%
Preparar apresentação pública para discussão
Descrever trabalho a realizar no semestre seguinte

## gantt 2semestre
2º Semestre
[8 empty] | Destaque de Período: | [6 empty] | -1 |  |  |  | Plano |  |  |  | Real |  |  | % Concluída |  |  |  |  | Real (para além do plano) | [8 empty] | % Concluída (para além do plano)
| PLANO | PLANO | REAL | REAL | PERCENTAGEM | PERÍODOS
ATIVIDADE | INÍCIO | DURAÇÃO | INÍCIO | DURAÇÃO | CONCLUÍDA | Mês 1 | [9 empty] | Mês 2 | [9 empty] | Mês 3 | [9 empty] | Mês 4 | [9 empty] | Mês 5 | [9 empty] | Mês 6
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Desenho de meios de avaliação | 1 | 20 |  |  | 0%
Implementação de meios de avaliação | 1 | 20 |  |  | 0%
Segunda fase de integração das ferramentas | 21 | 20 |  |  | 0%
Relatório final | 41 | 10 |  |  | 0%

## riscos
Risc Area | Preventative Measures | Recovery Measures
Equipment Failure | Ensure regular maintenance is undertaken | Use alternative sources/type of equipment as appropriate
Allow for sufficient funding for repairs
Indentify alternative sources/type of equipment
Data lost | Back-up data regularly
Publication of similar research | Regularly search electronic publications databases | Modify project
Continue literature review throughout candidature
Ensure timely submission
Personal issues interfere with progress | Take leave of absence (unless for sickness or bereavement) | Re-apply for admission when able to commit
Take annual leave
Take sick leave
Communicate with supervisor
Student leaves for employment / fails to complete on time fails to complete on time
Student loses interest
Dispute between student and supervisor
Supervisor takes excessive time to check final drafts
Student wants to submit thesis without supervisor approval